## Week-02152021
Weekly Plan and Status
Name |  | Steven Yuan
Report Period |  | April 12 ~ April 16, 2021
Status Report
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Test bench UI | 1 | Refactoring and adding new features | Completed | Add feature to the test bench based on the new protocol. Add support to handle asynchronous message from the device.
Test bench UI | 2 | Add stability test case for DWIN screen | Completed
Auto_Gen | 3 | C code generator | In Progress | dgus_widget.h, completed strings.h, completed strings.cpp, in progress
Test bench UI | 4 | V0.1.4 Release | In Progress
Plan for next week
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Auto_Gen | 1 | C code generator | In Progress | dgus_widget.h, completed strings.h, completed strings.cpp, in progress
Test bench UI | 2 | V0.1.4 Release | In Progress