## Week-02152021
Weekly Plan and Status
Name |  | Steven Yuan
Report Period |  | Feb, 22~26, 2021
Status Report
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Test bench | 1 | Create script to generate document | Completed
Test bench | 2 | Add uart feature to bench_run | Completed
Test bench | 3 | Update README on Bitbucket | In Progress | This is an ongoing work
Test bench | 4 | Create script to generate exe and pdf | Completed
Test bench | 5 | Add command 00 ~ 02 | Completed
Test bench | 6 | Add read cases from function feature | Completed
Plan for next week
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Test bench | 1 | Add multithreading feature | Not Started
Test bench | 2 | Update protocol, predefined table | Not Started
Test bench | 3 | Implement UI based on pyqt | Not Started