## Week-02152021
Weekly Plan and Status
Name |  | Steven Yuan
Report Period |  | March, 8~12, 2021
Status Report
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Test bench UI | 1 | Design the appearance of the UI | Completed | Design the new UI with Qt Designer
Test bench UI | 2 | Implement command functions of UI | In Progress | Program crashed unexpectedly
Test bench UI | 3 | Implement plotting feature of UI | In Progress
Plan for next week
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Test bench UI | 1 | Continue working on the UI | In Progress | Plan to finish the program this week