## Week-02152021
Weekly Plan and Status
Name |  | Steven Yuan
Report Period |  | March, 1~5, 2021
Status Report
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Test bench | 1 | Add multithreading feature to test bench | Completed
Test bench | 2 | Update protocol, predefined table | Completed
Test bench UI | 3 | Implement UI based on pyqt | In Progress
Documentation | 4 | Protocol for setting up STM32 Programmer | Completed
Test bench | 5 | Fix plotting issue | Completed
Test bench | 6 | Add reading Bryan’s test case feature | Completed
Plan for next week
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Test bench UI | 1 | Design the appearance of the UI | In Progress | May redesign a new interface.
Test bench UI | 2 | Implement command functions of UI | Not Started
Documentation | 3 | Apply Template to programmer documents | Not Started