## Week-02152021
Weekly Plan and Status
Name |  | Steven Yuan
Report Period |  | March, 22~26, 2021
Status Report
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Test bench UI | 1 | Add snapping cursor feature | Delayed
Dwin Screen | 2 | Fix black screen problem | Completed
Dwin Screen | 3 | Translate Serial communication command example and Dwin communication protocol to English | Completed
Dwin Screen | 4 | Verify Dwin screen ui and the communication protocol | Completed
Test bench UI | 5 | Improve performance of the ui | In Progress | Multiprocess and threading do not work as expected, will try different approach
Plan for next week
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Test bench UI | 1 | Try to use subprocess for the improvement | Not Started
Dwin Screen | 2 | Work with Dwin Eng to solve the screen configuration | In Progress