## Week-02152021
Weekly Plan and Status
Name |  | Steven Yuan
Report Period |  | March, 29~ April 2, 2021
Status Report
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Test bench UI | 1 | Use multiprocessing to improve the performance | Completed
Dwin Screen | 2 | Work with Dwin Eng to solve the touch screen problem | Completed
Plan for next week
Project | Task # | Description | Status | Comments/Issues | Planned Start Date | Planned Due Date | Actual Start Date | Actual Finish Date
Test bench UI (Test Case) | 1 | Add more feature to the test case command | In Progress | 1. For repeat set, continuously plot after a test case set is finished. 2. Keep the plot after it is done. 3. Show the status of the plot. 4. Show command received time. 5. Change x range to be number of test case.
Dwin Screen | 2 | Add feature to the screen interface | Not Started